## How to use
How to use the Project change and impact analysis template
Purpose of the document: The Document shell help to document improtant change requests decisions during the project development. It will help that decision for changes are collected in one document. How to use: The Project change and impact analysis works together with the Change tracking list. In the Change tracking list all changes are listed down. In the Project change and impact analysis from a detailed analysis of the change request will be done The PM is responsible that the change tracking list and the impact analysis form is correct filled out and always up to date

## 1. Analysis
1. Change Analysis
Project: | 5DH_DCDC
SAP PN: | EAP0060070000
Issue date: | 09.04.2023
Author: | Alexandru Stanciu
Jira Reference: | FDMDC-1175
1.1 Change request information
Change description
Increase threshold for Input Current Calibration on ATS1
From who / what is the change initiated (mark with x) and describe it
Customer
Vendor
R&D
Production | X
3rd Party
Reference to the Change (link to other documents or mails)
1. | https://jiradelta.deltaww.com/browse/FDMDC-1175
2.
3.
Justification for the change
Due to high failure rate caused by wrong calibration of the input current, production rate requested to open the specifications for the Input Current Calibration. Today, the units that are failed due to this cause, are being reworked so impacting the production calibration
Impact if the change will not be implemented
Production cannot fullfill the actual demand
Alternative to the described change
1.2. Change Committee
PM | Alexandru Stanciu
EE | Martin Prell
ME | Phillip Busch
SW | Dheeraj.k
Business Manager | Lars Krutmann
R&D Manager | Ulrich Nickel
NPI / Factory | Malinee
Quality | Chris Neitemeier
1.3. Change impact Analysis
|  | rating | Comment
Requirement specification: effected (intern / customer)? |  | y | input current calibration specifications are coming from RnD. Customer has no visibility on this parameter, but this has an impact on output current which is specified by customer
New Spec available? |  | n
Cost / Schedule Impact Analysis Required? |  | n
n
Feasability Study (23L2018W) updated and released? |  | n
Schedule affected? |  | n
Baselines affected? |  | n
Impact on Cost? |  | n
Impact on Schedule? |  | n
Impact on Resources? |  | n
Risk associated with implementing the change? |  | y | minor risk of not complying with the accuracy specifications
Risk associated with not implementing the change? |  | y | risk that the production flow will not be able to meet the demand
Costomer need to be informed? |  | n
Customer involvement needed? |  | n
Requote needed? |  | n
Vendor involvement needed? |  | n
Safety or FUSI impact? |  | n | the input current is not used in the any of the safety mechanism
Quality KPI |  | n
Reliability figures |  | n
Priority: (check one) |  | High |  | mid | low
1.4. Which departments need to be involved?
|  | check yes / no | Comment how involved
Electrical Engineer |  | y
Mechanical engineer |  | n
Software Engineer |  | y
Magnetic Design |  | n
Layout |  | n
EMI |  | n
Safety / Legal |  | n
QTS |  | n
Quality Department |  | y
CPC |  | n
DFM / IE |  | n
NPI / Factory |  | n
Customer |  | n
Vendor |  | n
1.5. Impact Analysis Results
Additional Resource Requirements (insert rows as needed): |  |  | Work Days | Cost
Total |  |  | 0 | 0
Additional NRE Requirements (insert rows as needed): |  |  | Work Days | Cost
Totals |  |  | 0 | 0
BOM cost impact |  |  | Work Days | Cost
Totals |  |  | 0 | 0
Schedule impact

## 2. Approval
2. Change Approval
2.1 Change committee decision
| Rating | Comment
Cost | not accepted
Design | not accepted
Schedule | not accepted
Quality | not accepted
Overall decision | not accepted
2.2 Steering commitee signatures
Date |  |  | Date | Date | Date | Date
BU head |  |  | Quality Manager | Business Manager | R&D Manager | PM
Distribute the final decision to all functions in the change committee and Involved Parties.

## 3. Execution
3. Execution
3.1. Implementation
| Status | Comment
Approval of Change commitee? | r
All involved parties informed? | r
Change list updated (link to file)? | r
Customer informed? | r
Quote accepted by customer? | r
Work packages defined (Jira link)? | r
Schedule updated | r
3.2. Integration
| Status | Comment
Work packages defined (Jira link)? | r
Delta product revision(s) | r
Customer product revision(s) | r
Qualification report available? | r
Customer qualification report? | r
Baseline updated? | r
r
3.3. Closing
| Status | Comment
SMCN / ECN (reference) | r
Production informed? | r
Customer approval | r
Change complete implemented | r

## Doc.-Rev.
Document history |  | Process Name: | Template Change request and impact analysis |  |  | Doc.-No.: | 23L2038Z
Document Revision: [num] | Change description: | Document drafted by: | Date: [dd.mmm.yyyy] | Document reviewed by: | Date: [dd.mmm.yyyy] | Document released by: | Date: [dd.mmm.yyyy]
00 | First release | J. Birkenfeld | 2012-01-12 | M. Prinz | 2012-01-12 | M. Hoelker | 2012-01-12
01 | improvement for new Change process | J. Birkenfeld | 2016-04-14 | U. Nickel | 2016-04-15 | M. Hoelker | 2016-04-15
02 | - add feasability Check - adjust rating | J. Birkenfeld | 2022-06-14 | M. Barth, A. Kroner | 2022-06-20 | A. Enns | 2022-06-20